## Project Schedule
90-DAY E-COMMERCE STARTUP IT PROJECT PLAN & GANTT CHART (WEEK 4 UPDATE)
Project: Aura Infrastructure Rollout - Deliverable 2 |  | Start Date: July 15, 2026 |  |  |  | Status Date: August 10, 2026 |  | Budget: $150,000
Course: CIS 599 Capstone Project |  | Student: Gerrell |  |  |  | Professor: Dr. [Professor's Name]
WBS | Task Name | Start Date | Start Day | End Day | Duration | Predecessors | Status | Resource | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90
1.0 | Phase 1: Planning and Site Design | 2026-07-15 | 1 | 15 |  |  | Completed | Gerrell
1.1 | Finalize office floorplans & locate server room | 2026-07-15 | 1 | 5 |  |  | Completed | Gerrell
1.2 | Select and purchase ISP business broadband | 2026-07-20 | 6 | 10 |  | 1.1 | Completed | Gerrell
1.3 | Draft hardware bill of materials (BoM) | 2026-07-25 | 11 | 15 |  | 1.2 | Completed | Gerrell
1.4 | Conduct business requirements scope review & CAB sign-off | 2026-07-26 | 12 | 15 |  | 1.3 | Completed | Gerrell
2.0 | Phase 2: Procurement and Cloud Provisioning | 2026-07-30 | 16 | 35 |  |  | In Progress | Gerrell
2.1 | Order corporate laptops and office networking hardware | 2026-07-30 | 16 | 20 |  | 1.3 | Completed | Gerrell
2.2 | Provision Shopify Plus sandbox database | 2026-08-04 | 21 | 28 |  | 2.1 | Completed | Gerrell
2.3 | Integrate ERP middleware with partner APIs | 2026-08-12 | 29 | 35 |  | 2.2 | In Progress | Gerrell
2.4 | Perform PCI-DSS and CCPA data privacy compliance audit | 2026-08-13 | 30 | 35 |  | 2.2 | In Progress | Gerrell
3.0 | Phase 3: Physical Installation and Cabling | 2026-08-19 | 36 | 60 |  |  | Not Started | Gerrell
3.1 | Install Cat6 Ethernet cabling in 2-story building | 2026-08-19 | 36 | 45 |  | 2.1 | Not Started | Gerrell
3.2 | Mount and configure Wi-Fi WAPs & core switches | 2026-08-29 | 46 | 55 |  | 3.1 | Not Started | Gerrell
3.3 | Set up firewall security profiles and office VPN | 2026-09-08 | 56 | 60 |  | 3.2 | Not Started | Gerrell
4.0 | Phase 4: Integration and System Testing | 2026-09-13 | 61 | 75 |  |  | Not Started | Gerrell
4.1 | End-to-end order routing testing (Shopify-ERP-Supplier) | 2026-09-13 | 61 | 68 |  | 2.3 | Not Started | Gerrell
4.2 | Test office network & run firewall failover tests | 2026-09-21 | 69 | 72 |  | 3.3 | Not Started | Gerrell
4.3 | Configure and verify local NAS backups | 2026-09-25 | 73 | 75 |  | 3.2 | Not Started | Gerrell
4.4 | Conduct User Acceptance Testing (UAT) with core staff | 2026-09-24 | 72 | 75 |  | 4.1, 4.2 | Not Started | Gerrell
5.0 | Phase 5: Go-Live and Training | 2026-09-28 | 76 | 90 |  |  | Not Started | Gerrell
5.1 | Onboard 10 staff members on new hardware/software | 2026-09-28 | 76 | 82 |  | 4.2 | Not Started | Gerrell
5.2 | Launch e-commerce storefront for beta customers | 2026-10-05 | 83 | 88 |  | 4.1, 5.1 | Not Started | Gerrell
5.3 | Conduct final project wrap-up and operational handoff | 2026-10-11 | 89 | 90 |  | 5.2 | Not Started | Gerrell